## Sheet1
Task | Developer | Time planned | Time used
ST02: Pick initial features/attributes | Klevi | 2 | 4
ST03: Research 4 different machine learning methods | Artur | 4 | 6
ST03: Prepare data. | Klevi | 2 | 4
ST03: Implement the chosen machine learning methods on a basic level | Artur | 6 | 6
ST02: Improve plotting | Klevi | 6 | 4
ST01: Divide the code up into modules | Artur | 4 | 1
ST02: Improve documentation. Probably write a PDF. | Klevi | 4 | 4
ST03: Evaluate the machine learning methods by running it on the data | Artur | 4 | 5
ST03: Document the process of choosing the methods. | Mo | 6 | 6
ST04: Set up documenation (probably using LaTeX) | Mo | 8 | 6
ST04: Make sure that as many OSs are supported as possible | Klevi | 4 | 2
ST04: Set up docker | Mo | 4 | 6
54