## Sheet1
Task | Developer | Time planned | Time used
Klevi
ST05: Decide on GUI tech | Klevi | 2 | 2
ST05: Plan the GUI functionalities | Klevi | 2 | 1
ST05: Plan GUI layout and work on it | Klevi | 7 | 7
ST05: Create visualizations for data (plots) | Klevi | 7 | 9
ST05: Predictor Agent Design | Mohammad | 2 | 3
ST05: Understand the requirement for Predictor Agent | Mohammad | 2 | 3
ST05: Research available APIs | Mohammad | 7 | 5
ST05: Evaluate the top candidate APIs | Mohammad | 7 | 7
ST04: Fine tune ML methods, hyperparameters | Artur | 7 | 6
ST04: Test ML methods based on the distance/time to target | Artur | 7 | 8
ST04: Research more about ML methods and work on data exploration | Artur | 4 | 4
54