## Sheet1
Task | Developer | Time planned | Time used
ST04: Integrate Docker to the project | Mohammad | 6
ST05: Integrate GUI with other systems | Klevi | 9
ST07: Integrate CI to the project | Mohammad | 6
ST06: Create Broker Agent system | Artur | 11 | 12
ST05: Work on GUI layout | Klevi | 9 | 12
ST05: Integrate Agent API with other systems | Mohammad | 6
ST06: Research Broker Agent system | Artur | 9 | 5
ST02: Potentially more data preparation to eliminate anomaly | Artur | 7 | 10
54